## Slide 1: Risk Management
AGENCY. ‘Action for Gender Equality, Non-Discrimination, Civil Society Strengthening and Youth Empowerment’
Supporting the capacity development of Tdh’s partners in the Gaza Strip
A webinar for Tdh’s Gazan CBO and NGO partners.

## Slide 2: Ahlan Wa Sahlan
Welcome to this Webinar produced by Terre des hommes Foundation, Lausanne, as part of its support to its AGENCY partners’ capacity building.

## Slide 3: Some guidelines for this session
When you are not talking, turn on mute to prevent feedback.
Keep your camera on if you can. If you have bandwidth problem, turn your camera off.
Ask questions at the end of the webinar. Keep a notepaper and pen with you to remind yourself what you want to ask.

## Slide 4: The purpose of this Webinar
This Webinar outlines the basic principles and strategies that can be applied by Tdh’s CBO and NGO partners in Gaza to manage their risks.
It should help Tdh’s partners to:
1. Identify the major risks that apply to their charity
2. Make decisions about how to respond to the risks they face

## Slide 5: Expectations from the Webinar
This is a short snapshot of a complex issue. We hope:
That it will be interesting and thought provoking.
That it will be useful.
That it will help you reconsider risk in the work you do.

## Slide 6: The agenda for today
What is Risk Management and why is it important?
What types of risks do charities face in the Gaza Strip and how do we categorize them?
Managing risk
Risk tolerant, risk averse. What’s the difference?
Establishing a risk policy
Identifying and assessing risks
Developing a heat map
Periodic monitoring and assessment

## Slide 7: What is risk management and why is it important?
Risk management is the process of identifying, monitoring and managing potential risks in order to minimize the negative impact they may have on an organization.
Identifying and managing the possible and probable risks that a charity may face is a key part of effective governance and good management for charities of all sizes and complexity. By managing risk effectively, NGOs can help ensure that:
Significant risks are known and monitored, enabling the organisation to make informed decisions and take timely action.
The charity makes the most of opportunities and develops them with the confidence that risks are understood and can be be managed.
Forward and strategic planning are improved.
The charity’s aims are achieved more successfully.
It is an essential part of accountability to the charity’s supporters, to the wider public and to donors / funders and partners.

## Slide 8: Risks facing NGOs and CBOs in the Gaza Strip
Risk category | Examples
Governance risks | Inappropriate organisational structure. For example, SMT members sitting as board members, or board members beholden to management. There should be clear distance between Governance (the board) and Management (the SMT). The board lacks relevant skills or commitment. Conflicts of interest within the board or between it and the SMT.
Operational risks | Lack of beneficiary welfare or safety. No commitment to health and safety, or to promoting a strong safeguarding culture. Poor contract bidding. You budget too low, or you make programmatic promises you can’t keep. You under deliver, or you ask for a funding review. You lose the trust of your funders. You suffer reputational damage. Poor staff recruitment and training. You don’t have the tools to do the job. The risk of loss resulting from failed internal processes, people or systems or external events. Examples include global crises, IT systems failure, data breaches, fraud, loss of people and litigation, among others.
Financial risks | Poor financial management and reporting systems. Inaccurate and/or insufficient financial information leads to poor decision making. Short term funding leading to perpetual crises. Inadequate reserves and cash flow. Dependency on limited income sources.
External risks | Poor public perception and reputation. Turbulent political economic or security environment. Unclear, or changing government policy. New and demanding international funder requirements.
Compliance with law and regulation | Poor knowledge of the legal responsibilities of an employer. Poor knowledge of regulatory requirements of particular activities (e.g. fund-raising, health and safety, safeguarding operating vehicles).

## Slide 9: Other risks NGOs and CBOs face in the Gaza Strip
Charities working in the Gaza Strip will face some level of risk in most of the things they do. The diverse nature of the sector and its activities – and the fact that they work in times of political, economic and security insecurity - means that Tdh’s partners face different types of risk and levels of exposure.
An essential question for Tdh’s partners when considering risk is whether or not they can continue to meet the needs of beneficiaries now and in the future. For example, in a period of political, economic and security uncertainty, the major financial risks for a charity might be:
Loss or suspension of registration.
Hostility or threats to employees or those associated with it.
Suspension or loss of funding.
An unforeseen rise in demand for their services.
Generally, risk will need to be considered in terms of the wider environment in which the charity operates. These include:
Political: Disputes over local / national political legal legitimacy. The danger of perceived ‘factionalism’. International demands including a proven commitment to anti terror legislation which may require the screening of the organisation and senior staff for ‘proscribed’ or ‘designated’ status.
Economic: Poverty. The blockade. The short- and longer-term impacts of war. Denial of external funding. Short term funding. Conditional funding from international partners.
Security: Perpetual insecurity. The threat of war.

## Slide 10: The International Organization for Standardization’s (ISO) 5 step guide to the risk management process.
Identify
Identify the risks.
Analyze
Analyze the likelihood and impact of each one.
Prioritize
Prioritize risks based on business objectives.
Treat
Treat (or respond to) the risk conditions.
Monitor
Monitor results and adjust as necessary.

## Slide 11: What risks do you face in your work?

## Slide 12: Assessing risk
Identified risks need to be put into perspective in terms of the potential severity of their impact and likelihood of their occurrence. Assessing and categorising risks helps in prioritising and filtering them, and in establishing whether any further action is required. One method is to look at each identified risk and decide how likely it is to occur and how severe its impact would be on the charity if it did occur.
This approach attempts to map risk as a product of the likelihood of an undesirable outcome and the impact that an undesirable outcome will have on the charity’s ability to achieve its operational objectives. It enables the board of governors and the SMT to identify those risks that fall into the major risk category identified by the risk management statement.

## Slide 13: Risk Likelihood
Descriptor | Score | Example
Remote | 1 | May only occur in exceptional circumstances
Unlikely | 2 | Expected to occur in a few circumstances
Possible | 3 | Expected to occur in some circumstances
Probable | 4 | Expected to occur in many circumstances
Highly probable | 5 | Expected to occur frequently and in most circumstances

## Slide 14: Assessing Impact
Descriptor | Score | Impact on service and reputation
Insignificant | 1 | • No impact on service • No impact on reputation • Complaint unlikely • Litigation risk remote
Minor | 2 | • Slight impact on service • Slight impact on reputation • Complaint possible • Litigation possible
Moderate | 3 | • Some service disruption • Potential for adverse publicity - avoidable with careful handling • Complaint probable • Litigation probable
Major | 4 | • Service disrupted • Adverse publicity not avoidable (local media) • Complaint probable • Litigation probable
Extreme / Catastrophic | 5 | • Service interrupted for significant time • Major adverse publicity not avoidable (national media) • Major litigation expected • Resignation of senior management and board • Loss of beneficiary confidence

## Slide 15: Developing a heat map
In the table below, the score for Livelihood is multiplied by the score for Impact.
Impact | Likelihood - Remote 1 | Likelihood - Unlikely 2 | Likelihood - Possible 3 | Likelihood - Probable 4 | Likelihood - Highly probable 5
Impact - Insignificant 1 | 1 | 2 | 3 | 4 | 5
Impact - Minor 2 | 2 | 4 | 6 | 8 | 10
Impact - Moderate 3 | 3 | 6 | 9 | 12 | 15
Impact - Major 4 | 4 | 8 | 12 | 16 | 20
Impact - Extreme / Catastrophic 5 | 5 | 10 | 15 | 20 | 25

## Slide 16: The Heat Map
The image below shows the same heat map with colour codes.
The colour codes are:
Red - major or extreme/catastrophic risks that score 15 or more
Yellow - moderate or major risks that score between 8 and 14
Blue - minor or insignificant risks scoring 7 or less
IMPACT | Extreme / Catastrophic 5 | 5 | 10 | 15 | 20 | 25
 | Major 4 | 4 | 8 | 12 | 16 | 20
 | Moderate 3 | 3 | 6 | 9 | 12 | 15
 | Minor 2 | 2 | 4 | 6 | 8 | 10
 | Insignificant 1 | 1 | 2 | 3 | 4 | 6
 |  | Remote 1 | Unlikely 2 | Possible 3 | Probable 4 | Highly Probable 5
 | LIKELIHOOD |  |  |  |  | 

## Slide 17: Evaluating what action needs to be taken on the risks
Where major risks are identified, the organisation will need to make sure that appropriate action is being taken to manage them. This review should include assessing how effective existing controls are.
For each of the major risks identified, board of governors will need to consider any additional action that needs to be taken to manage the risk, either by lessening the likelihood of the event occurring, or lessening its impact if it does. The following are examples of possible actions:
  By approaching your donor to discuss the risk and seek advice, or approval for a preferred course of action.
  The risk may need to be avoided by ending that activity (e.g., stopping work).
  The risk could be transferred to a third party, for example by outsourcing the work (and the risk) to others.
  The risk could be shared with others (e.g., a joint venture project).
  The risk can be reduced or eliminated by establishing or improving control procedures (e.g., internal financial controls, controls on recruitment, personnel policies).
  The risk may need to be insured against (this often happens for residual risk, e.g., employers' liability, third party liability, theft, fire).
  The risk may be accepted as being unlikely to occur and/or of low impact and therefore will just be reviewed annually.

## Slide 18: Periodic monitoring and assessment
Risk management is a dynamic process. This means that new risks are addressed as they arise.
Risk management is not a one-off event and should be seen as a process that will require monitoring and assessment. Staff will need to take responsibility for implementation.
There needs to be communication with staff at all levels to ensure that individual and group responsibilities are understood and embedded into the culture of the charity. A successful process will involve ensuring that:
New risks are properly reported and evaluated.
Risk aspects of significant new projects are considered as part of project appraisals.
Any significant failures of control systems are properly reported and actioned.
There is an adequate level of understanding of individual responsibilities for both implementation and monitoring of the control systems.
Any further actions required are identified.
The Senior Management Team (SMT) and the Board of governors are fully informed in order that they can consider how best to react.

## Slide 19: Conclusions and Next Steps
How, if at all, can you apply this learning?
What will YOU do?
What will you ask others to do?
What would you like Tdh to do?

## Slide 20: Questions and Answers
Please feel free to ask questions.
I will do my best to answer them, but, if I cannot, I will research the question and reply to you later.

## Slide 21: Annexes
The following sides list several risks across a range of sectors that will possibly be faced by Tdh’s Gazan partners.
They are provided for reference but will not be presented in this Webinar.

## Slide 22: Governance Risks
Potential risk | Potential impact | Steps to mitigate risk
The charity lacks direction, strategy and forward planning | The charity drifts with no clear objectives, priorities or plans Issues are addressed piecemeal with no strategic reference Needs of beneficiaries not fully addressed Financial management difficulties Loss of reputation | Create a strategic plan which sets out the key aims, objectives and policies Create financial plans and budgets Use job plans and targets Monitor financial and operational performance Get feedback from beneficiaries and funders
The Board lacks relevant skills or commitment | Charity becomes moribund or fails to achieve its purpose Decisions are made bypassing the board Resentment or apathy amongst staff Poor decision making reflected in poor value for money on service delivery | Review and agree skills required Draw up competence framework and job descriptions Implement board member training and induction Review and agree recruitment processes
The Board dominated by one or two individuals, or by connected individuals | The Board cannot operate effectively as strategic body Decisions made outside of the board Conflicts of interest Pursuit of personal agenda Culture of secrecy or deference Arbitrary over-riding of control mechanisms | Consider the structure of the board and its independence Agree mechanisms to manage potential conflicts of interest Review and agree recruitment and appointment processes in line with governing document Agree procedural framework for meetings and recording decisions
Board members are benefiting from charity (e.g. remuneration) | Poor reputation, morale and ethos Adverse impact on overall control environment Conflicts of interest Possibility of regulatory action | Ensure legal authority for payment or benefit Consider alternative staffing arrangements Implement terms and procedures to authorise/approve expenses and payments Agree procedures and methods to establish fair remuneration
Conflicts of interest | Charity unable to pursue its own interests and agenda Decisions may not be based on relevant considerations Impact on reputation Private benefit | Agree protocol for disclosure of potential conflicts of interest Put in place procedures for standing down on certain decisions Review recruitment and selection processes
Ineffective organisational structure | Lack of information flow and poor decision making procedures Remoteness from operational activities Uncertainty as to roles and duties Decisions made at inappropriate level or excessive bureaucracy | Use organisation chart to create a clear understanding of roles and duties Delegation and monitoring should be consistent with good practice and constitutional or legal requirements Review structure and the need for constitutional change
Loss of key staff | Experience or skills lost Operational impact on key projects and priorities Loss of contact base and corporate knowledge | Succession planning Document systems, plans and projects Implement training programmes Agree notice periods and handovers Review and agree recruitment processes
Reporting to board members (accuracy, timeliness and relevance) is inadequate | Inadequate information resulting in poor quality decision making Failure of board members to fulfil their control functions The board becomes remote and ill informed | Put in place proper strategic planning, objective setting and budgeting processes Timely and accurate project reporting Timely and accurate financial reporting Assess and review projects and authorisation procedures Have regular contact between board members and senior staff and managers

## Slide 23: Operational Risks
Contract risk | • Onerous terms and conditions • Liabilities for non performance • Non-compliance with charity’s objects • Unplanned subsidy of public provision | • Create cost/project appraisal procedures • Agree authorisation procedures • Get professional advice on terms and conditions • Put in place performance monitoring arrangements • Consider insurable risks cover
Competition from similar organisations | • Loss of contract income • Reduced fund-raising potential • Reduced public profile • Profitability of trading activities | • Monitor and assess performance and quality of service • Review market and methods of service delivery • Agree fund-raising strategy • Ensure regular contact with funders • Monitor public awareness and profile of charity
Suppliers, dependency, bargaining power | • Dependency on key supplier • Lack of supplier to meet key operational objectives • Non-competitive pricing/quotes • Insufficient buying power | • Use competitive tendering for larger contracts • Put in place procedures for obtaining quotations • Authorised suppliers listing • Monitor quality/timeliness of provision • Use service level agreements • Consider use of buying consortia
Employment issues | • Employment disputes • Health and safety issues • Claims for injury, stress, harassment, unfair dismissal • Equal opportunity and diversity issues • Adequacy of staff training • Child protection issues • Low morale • Abuse of vulnerable beneficiaries | • Review recruitment processes • Agree reference and qualification checking procedures, job descriptions, contracts of employment, appraisals and feedback procedures • Implement job training and development • Implement health and safety training and monitoring • Be aware of employment law requirements • Implement staff vetting and legal requirements (e.g. DBS checks) • Agree a whistle-blowing policy
High staff turnover | • Loss of experience or key technical skills • Recruitment costs and lead time • Training costs • Operational impact on staff morale and service delivery | • Review interview and assessment processes • Agree fair and open competition appointment for key posts • Agree job descriptions and performance appraisal and feedback systems • Conduct ‘exit’ interviews • Review rates of pay, training, working conditions, job satisfaction
Health, safety and environment | • Staff injury • Product or service liability • Ability to operate (see Compliance risks) • Injury to beneficiaries and the public | • Comply with law and regulation • Train staff and compliance officer • Put in place monitoring and reporting procedures
Procedural and systems documentation | • Lack of awareness of procedures and policies • Actions taken without proper authority | • Properly document policies and procedures • Audit and review of systems
Information technology | • Systems fail to meet operational need • Failure to innovate or update systems • Loss/corruption of data e.g. donor base • Lack of technical support • Breach of data protection law | • Appraise system needs and options • Appraise security and authorisation procedures • Implement measures to secure and protect data • Agree implementation and development procedures • Use service and support contracts • Create disaster recovery procedures • Consider outsourcing • Review insurance cover for any insurable loss
Potential risk | Potential impact | Steps to mitigate risk

## Slide 24: Financial Risks
Potential risk | Potential impact | Steps to mitigate risk
Budgetary control and financial reporting | • Budget does not match key objectives and priorities • Decisions made on inaccurate financial projections or reporting • Decisions made based on unreliable costing data or income projections • Inability to meet commitments or key objectives • Poor credit control • Poor cash flow and treasury management • Ability to function as going concern | • Link budgets to business planning and objectives • Monitor and report in a timely and accurate way • Use proper costing procedures for product or service delivery • Ensure adequate skills base to produce and interpret budgetary and financial reports • Agree procedures to review and action budget/cash flow variances and monitor and control costs • Regularly review reserves and investments
Reserves policies | • Lack of funds or liquidity to respond to new needs or requirements • Inability to meet commitments or planned objectives • Reputational risks if policy cannot be justified | • Link reserves policy to business plans, activities and identified financial and operating risk • Regularly review reserves policy and reserve levels
Cash flow sensitivities | • Inability to meet commitments • Lack of liquidity to cover variance in costs • Impact on operational activities | • Ensure adequate cash flow projections (prudence of assumptions) • Identify major sensitivities • Ensure adequate information flow from operational managers • Monitor arrangements and reporting
Dependency on income sources | • Cash flow and budget impact of loss of income source | • Identify major dependencies • Implement adequate reserves policy • Consider diversification plans
Foreign currency | • Currency exchange losses • Uncertainty over project costs • Cash flow impact on operational activities | • Ensure proper cash flow management and reserves policy • Use currency matching (cost to charity in home currency) • Consider forward contracts for operational needs (hedging)
Compliance with donor imposed restrictions | • Funds applied outside restriction • Repayment of grant • Future relationship with donor and beneficiaries • Regulatory action | • Implement systems to identify restricted receipts • Agree budget control, monitoring and reporting arrangements
Fraud or error | • Financial loss • Reputational risk • Loss of staff morale • Regulatory action • Impact on funding | • Review financial control procedures • Segregate duties • Set authorisation limits • Agree whistle-blowing anti fraud policy • Review security of assets • Identify insurable risks

## Slide 25: Environmental or External Factors
Potential risk | Potential impact | Steps to mitigate risk
Public perception | Impact on voluntary income Impact on use of services by beneficiaries Ability to access grants or contract funding | • Communicate with supporters and beneficiaries • Ensure good quality reporting of the charity’s activities and financial situation • Implement public relations training/procedures
Adverse publicity | Loss of donor confidence or funding Loss of influence Impact on morale of staff Loss of beneficiary confidence | Implement complaints procedures (both internal and external) Agree proper review procedures for complaints Agree a crisis management strategy for handling - including consistency of key messages and a nominated spokesperson
Relationship with funders | Deterioration in relationship may impact on funding and support available | Ensure regular contact and briefings to major funders Report fully on projects Meet funders’ terms and conditions
Demographic consideration | Impact of demographic distribution of donors or beneficiaries Increasing or decreasing beneficiary class Increasing or decreasing donor class | Profile donor base Profile and understand beneficiary needs Use actuarial analysis to establish future funding requirements
Government policy | Availability of contract and grant funding Impact of tax regime on voluntary giving Impact of general legislation or regulation on activities undertaken Role of voluntary sector | Monitor proposed legal and regulatory changes Consider membership of appropriate umbrella bodies

## Slide 26: Compliance risk. Rules and Regulations
Potential risk | Potential impact | Steps to mitigate risk
Compliance with legislation and regulations appropriate to the activities, size and structure of the charity | Fines, penalties or censure from licensing or activity regulators Loss of licence to undertake particular activity (see operational risks) Employee or consumer action for negligence Reputational risks | Identify key legal and regulatory requirements Allocate responsibility for key compliance procedure Put in place compliance monitoring and reporting Prepare for compliance visits Obtain compliance reports from regulators (where appropriate) - auditors and staff to consider and action at appropriate level
Regulatory reporting requirements: Financial and other reporting requirements will be dependent on how the charity is constituted and may also vary according to funding arrangements | Regulatory action Reputational risks Impact on funding | Review and agree compliance procedures and allocation of staff responsibilities
Taxation | Penalties, interest and ‘back duty’ assessments Loss of income e.g. failure to utilise gift aid arrangements Loss of mandatory or discretionary rate relief Failure to utilise tax exemptions and reliefs | Review tax compliance procedures (income tax and others pertaining to the charity (VAT, corporation tax, etc). File timely tax returns Understand exemptions and reliefs available (direct tax and VAT) Take advice on employment status and contract terms and tax Implement budget and financial reporting identifying trading receipts, and tax recoveries
Professional advice | Lack of investment strategy or management Failure to optimise fiscal position Contract risks Failure to address compliance risks | Identify and ensure access to professional advice Identify issues where advice is required Conduct compliance reviews